## Team Roles
Team Member | Role | Responsibilites | Due Date | Status | Notes
Sheila | Data Analyst
|  | Lead data collection and cleanup | 2025-01-18 | Completed
|  | Assist with documenting Details on README MD file | 2025-01-25 | In Progress
|  | Perform statistical analysis | 2025-01-24 | In Progress
|  | Support visualization creation | 2025-01-24 | In Progress
|  | Document analysis methodology ReadMe / Powerpoint | 2025-01-25 | In Progress
|  | Contribute to final presentation | 2025-01-26 | Pending
Michael Brady | Data & Statistical Analyst
|  | Research, Intake Moon Phase & Crime datasets, prepare for analysis | 2025-01-19 | Completed
|  | Correlate Moon Phase crime data (Austin, Den. Chicago) | 2025-01-21 | Completed
|  | Normalise and Merge data | 2025-01-21 | In Progress
|  | Create visualizations | 2025-01-22 | In Progress
|  | Ensure proper labeling and documentation | 2025-01-24 | In Progress
|  | Investigate and support statistical analysis | 2025-01-25 | In Progress
|  | Assist with presentation design | 2025-01-25 | In Progress
Raymond | Project Manager,Visualization, & Documentatio | Coordinate team efforts and track progress | 2025-01-26 | In Progress
|  | Review and provide feedback on all deliverables | 2025-01-23 | In Progress
|  | Refine 6-8 required visualizations | 2025-01-24 | Outstanding
|  | Review & Assist if needed on presentation slides | 2025-01-25 | In Progress
|  | Primary on README file w/ Sheila | 2025-01-24 | In Progress
|  | Ensure all requirements are met | 2025-01-25 | In Progress
|  | Final quality checks | 2025-01-25 | Start 1-24-25

## Requirements
Lunar Madness Project Requirements | Point Value | Fulfilled ? | Notes | Next Step(s)
Software Version Control (10 points)
Repository is created on GitHub | 2 | Yes
Files are frequently committed to the repository | 3 | Yes
Commit messages include an appropriate level of detail | 2 | Yes
Repository is organized and includes relevant information and project files | 3 | TBD
Documentation (10 points)
Code is well commented with concise, relevant notes | 3 | TBD
GitHub README file includes a concise project overview | 2 | InProgress
GitHub README file includes detailed usage and installation instructions | 2 | InProgress
GitHub README includes either examples of the application, or the results and a summary of the analysis | 3 | InProgress
Analysis and Conclusion (30 points)
Findings are strongly supported with numbers and visualizations (10 points). | 10 | 1-23-25 Team
Write-up summarizes major findings and implications at a professional level (10 points). | 10 | 1-23-25 Team
Each question in the project proposal is answered with precise descriptions and findings (5 points). | 5 | 1-23-25 Team
Each question response is supported with a well-discerned statistical analysis from lessons, such as:
aggregation, correlation, comparison, summary statistics, sentiment analysis, and time series analysis (5 points). | 5 | 1-23-25 Team
Visualizations (20 points)
6–8 visualizations of data (at least two per question) (10 points). | 10 | InProgress
Clear and accurate labeling of images (5 points). | 5 | InProgress
Visualizations supported with ample and precise explanation (5 points). | 5 | InProgress
Presentation Requirements (30 points)
An executive summary or overview of the project and project goals (5 points). | 5 | InProgress
An overview of the data collection, cleanup, and exploration processes (5 points). | 5 | 1-23-25 Team
The approach that your group took in achieving the project goals (5 points). | 5 | 1-23-25 Team
Raise questions that surfaced, ID what to research next, or for future development (5 points). | 5 | 1-23-25 Team
The results and conclusions of the application or analysis (5 points). | 5 | 1-23-25 Team
Slides effectively demonstrate the project (3 points). | 3 | InProgress
Slides are visually clean and professional (2 points) | 2 | Yes